## Sheet1
Date	Tasks	Status
04/03/24	Study about the domain and List down the functionalities and entities
	Design database schema/setup Postgres sql use and get it reviewed
	Define the services and draw an UML-class diagram for services
	plan endpoints for garage management initialize a git repo
	plan the git branches and workflow

11/03/24	Implement authentication and authorization, define roles and access for the endpoints
	Start back end implementation and create entities and repositories
	implement curd operations for the entities
	Implement Appointment Booking functionality
	Implement Work Order service

18/03/24	implement Billing management service
	Test backend api using post man
	Explore kafka
	Set up Ant Design Pro(front-end setup)
	create a git repo and initialize the frontend

25/03/24	Start designing front end UIs
	Implementing front-end functionality
	Integrate the frontend with backend
	Test Entire application
	Deploy application in Docker